## Backlog
Project Title: Hydra Tanks Current Release #: v0.5 Current Sprint #: 4 (see tabs below)
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that <outcome> | Estimate | Assigned To | Sprint #
| Funtional Requirements |  |  |  |  | Jamie Lewis
1 | Controls | As a player | I would like to control the tank with different control types | so that I can easily maneuver and shoot | 4 |  | 1
2 | Enemy Spawning | As a player | I would like enemies to dynamically spawn on the map | so that the game feels unpredictable and challenging | 2 |  | 1
3 | Scoring System | As a player | I would like to see my score in real-time on the game screen | so that I can track my progress during a level | 2 |  | 1
4 | Audio | As a player | I would like to hear various sound effects | so that I can have an immersive experience | 2 |  | 1
5 | Graphics | As a player | I would like to see special effects for hits, power-ups, etc | so that I can have an immersive experience | 2 |  | 1
6 | Levels | As a player | I would like to load a level | so that I can start a game | 2 |  | 1
7 | Scoring | As a player | I would like to see my high score from each level | so that I can compare my progress between levels | 2 |  | 2
8 | Levels | As a player | I would like to choose from multiple levels | so that I can have different levels of difficulty | 8 |  | 2,3
9 | Audio | As a player | I would like to adjust volume levels | so that I can customize my experience | 2 |  | 2
13 | Menu | As a player | I would like to see the Controls and How To Play | so that I can get into the game faster and not have to figure things out for myself | 4 |  | 3
Non-Functional Requirements
0 | Project Setup | As a developer | I want to setup a new Unity project | so that I can start with a clean slate and import scripts and assets as needed | 2 |  | 1
10 | UI | As a developer | I would like the user interface to be intuitive and easy to navigate | so that it enhances player satisfaction and retention | 4 |  | 2
11 | Scoring | As a developer | I would like to save the player's high score for each level | so that the player can see their record scores | 2 |  | 2
12 | UI | As a developer | I would like text and buttons to scale appropriately with screen size | so that it provides a consistent experience | 2 |  | 3
14 | Level Manager | As a developer | I would like to balance the difficulty of the game across levels | so that the player experience is enhanced | 2 |  | 4
15 | Cleanup | As a developer | I would like to perform code cleanup and refactoring | so that my project is bug-free and maintainable | 2 |  | 4
|  | TOTAL HOURS ESTIMATE |  |  | 44
|  | % of Project Tasks Complete (by # of tasks, then by # of estimated hours) |  |  | 100% | 100%

## Sprint 1
Project: | Hydra Tanks
Sprint # | 1
|  |  |  | DATE: | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25
| User Story ID | User Story | Task | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Total Hours per Task |  | Task Complete?
| 0 | I want to setup a new Unity project so that I can start with a clean slate and import scripts and assets as needed | Setup new Unity project | 2 |  | 1 | [5 empty] | 1 |  | Yes
| 1 | I would like to control the tank with different control types so that I can easily maneuver and shoot | Input Manager | 4 |  |  | 6 |  |  |  |  | 6 |  | Yes
| 2 | I would like enemies to dynamically spawn on the map so that the game feels unpredictable and challenging | Level Manager | 2 |  |  |  | 3 |  |  |  | 3 |  | Yes
| 3 | I would like to see my score in real-time on the game screen so that I can track my progress during a level | Level Manager | 2 |  |  |  |  | 3 |  |  | 3 |  | Yes
| 4 | I would like to hear various sound effects so that I can have an immersive experience | Audio Manager | 2 |  | 1 | [5 empty] | 1 |  | Yes
| 5 | I would like to see special effects for hits, power-ups, etc so that I can have an immersive experience | Sprite Assets, Animations | 2 |  | 1 | [5 empty] | 1 |  | Yes
| 6 | I would like to load a level so that I can start a game | Menu System, Level Manager | 2 |  | 1 |  |  | 2 |  |  | 3 |  | Yes
| Ideal - Remaining efforts in uninterrupted working hours. |  |  | 16 | 14 | 10 | 8 | 6 | 4 | 2 | 0 | Total Hours Worked | 18
| Actual - RemainingEfforts in uninterrupted working hours. |  |  | 16 | 16 | 12 | 6 | 3 | -2 | -2 | -2
|  |  | Total Daily Hours |  | 0 | 4 | 6 | 3 | 5 | 0 | 0 | % of Sprint Tasks Complete |  | 100

## Sprint 2
Project: | Hydra Tanks
Sprint # | 2
|  |  |  | DATE: | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-02 | 2024-03-03
| User Story ID | User Story | Task | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Total Hours per Task |  | Task Complete?
| 7 | I would like to see my high score from each level so that I can compare my progress between levels | High Scores Menu Screen | 2 |  |  |  |  | 2 |  |  | 2 |  | Yes
| 8 | I would like to choose from multiple levels so that I can have different levels of difficulty | Level Building | 8 | [6 empty] | 4 | 4 |  | Partially
| 9 | I would like to adjust volume levels so that I can customize my experience | Hook up Audio Settings | 2 | [5 empty] | 2 |  | 2 |  | Yes
| 10 | I would like to save the player's high score for each level so that the player can see their record scores | Save System - High Scores | 2 |  |  |  |  | 2 |  |  | 2 |  | Yes
| 11 | I would like the user interface to be intuitive and easy to navigate so that it enhances player satisfaction and retention | UI - Add more button functionality | 4 | [5 empty] | 4 |  | 4 |  | Yes
| Ideal - Remaining efforts in uninterrupted working hours. |  |  | 18 | 16 | 14 | 12 | 10 | 8 | 4 | 0 | Total Hours Worked | 14
| Actual - RemainingEfforts in uninterrupted working hours. |  |  | 18 | 18 | 18 | 18 | 18 | 14 | 8 | 4
|  |  | Total Daily Hours |  | 0 | 0 | 0 | 0 | 4 | 6 | 4 | % of Sprint Tasks Complete |  | 90%

## Sprint 3
Project: | Hydra Tanks
Sprint # | 3
|  |  |  | DATE: | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10
| User Story ID | User Story | Task | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Total Hours per Task |  | Task Complete?
| 8 | I would like to choose from multiple levels so that I can have different levels of difficulty | Level Building | 4 |  |  |  |  | 2 | 4 |  | 6 |  | Yes
| 12 | I would like text and buttons to scale appropriately with screen size so that it provides a consistent experience | UI - polishing | 2 |  |  |  | 2 |  |  |  | 2 |  | Yes
| 13 | I would like to see the Controls and How To Play so that I can get into the game faster and not have to figure things out for myself | Menu System - Add a new screen | 4 |  |  |  |  | 4 |  |  | 4 |  | Yes
| Ideal - Remaining efforts in uninterrupted working hours. |  |  | 10 | 10 | 10 | 10 | 8 | 4 | 2 | 0 | Total Hours Worked | 12
| Actual - RemainingEfforts in uninterrupted working hours. |  |  | 10 | 10 | 10 | 10 | 8 | 2 | -2 | -2
|  |  | Total Daily Hours |  | 0 | 0 | 0 | 2 | 6 | 4 | 0 | % of Sprint Tasks Complete |  | 100

## Sprint 4
Project: | Hydra Tanks
Sprint # | 3
|  |  |  | DATE: | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-17
| User Story ID | User Story | Task | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Total Hours per Task |  | Task Complete?
| 14 | I would like to balance the difficulty of the game across levels so that the player experience is enhanced | Level Manager - game balancing | 4 |  |  |  |  | 2 | 2 |  | 4 |  | Yes
| 15 | I would like to perform code cleanup and refactoring so that my project is bug-free and maintainable | Code cleanup, minor refactoring, commenting | 4 | [5 empty] | 4 | 2 | 6 |  | Yes
| Ideal - Remaining efforts in uninterrupted working hours. |  |  | 8 | 8 | 8 | 8 | 8 | 4 | 2 | 0 | Total Hours Worked | 10
| Actual - RemainingEfforts in uninterrupted working hours. |  |  | 8 | 8 | 8 | 8 | 8 | 6 | 0 | -2
|  |  | Total Daily Hours |  | 0 | 0 | 0 | 0 | 2 | 6 | 2 | % of Sprint Tasks Complete |  | 100